Cost Estimate

Designing an Electronic Performance Support System (EPSS)

for

WidgetMart

2345 London Avenue

London, NJ  00001

April 5, 2013

WidgetMart EPSS Cost Estimate

| WBS No. | Activity Name | Work Effort/ Total Resource Hours | Resource Name Resource Rate per hour Resource Hours Resource Total Rate | Activity Estimate | Indirect Cost @ 50% of activity | Travel Cost | Reserve @ 20% of activity | Total Estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Initiation - EPSS | 144 | Davey @ $55: 67.2 hours = $3696 Ellen @ $49: 19.2 hours = $940.80 Barry @ $ 45: 19.2 hours = $864 Tim @ $47: 19.2 hours = $902.40 Josie @ $47: 19.2 hours = $902.40 | $7,305.60 | $3,652.80 | 0 | $1,416.12 | $10,913.40 |
| 1.2 | Develop Project Plan | 184 | Davey @ $55: 120 hours = $6,600 Ellen @ $49: 16 hours = $784 Barry @ $ 45: 16 hours = 720 Tim @ $47: 16 hours = 752 Josie @ $47: 16 hours = $752 | $9,608 | $4,804 | 0 | $1,921.60 | $16,334 |
| 1.3.1 | Contractor Procurement | 40 | Davey @ $55: 40 hours = $2,200 | $2,200 | $1,100 | 0 | $440 | $3,740 |
| 1.3.2 | Project Team Kick-Off Meeting | 64 | Davey @ $55: 8 hours = $440 Ellen @ $49: 8 hours = $392 Barry @ $ 45: 8 hours = $360 Tim @ $47: 8 hours = $376 Josie @ $47: 8 hours = $376 Developer 1 @ $35: 8 hours = $280 Developer 2 @ $35: 8 hours = $280 ID Consultant @ $50: 8 hours = $400 | $2,904 | $1,452 | 0 | $580.80 | $4,937 |

| WBS No. | Activity Name | Work Effort/ Resource Hours | Resource Name Resource Rate per hour Resource Hours Resource Total Rate | Activity Estimate | Indirect Cost @ 50% of activity | Travel Cost | Reserve @ 20% of activity | Total Estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.3.3 | User Requirements | 120 | Davey @ $55: 40 hours = $2,200 Ellen @ $49: 80 hours = $3,920 | $6,120 | $3,060 | 0 | $918 | $10,098 |
| 1.3.4 | Data Clean-Up | 160 | Tim @ $47: 80 hours = $3,760 Josie @ $47: 80 hours = $3,760 | $7,520 | $3,760 | 0 | $1,224 | $12,504 |
| 1.3.5 | EPSS Phase 1 Design | 472 | Ellen @ $49: 64 hours = $3,136 Barry @ $ 45: 64 hours = $2,880 Josie @ $47: 80 hours = $3,760 Developer 1 @ $35: 104 hours = $3,640 Developer 2 @ $35: 104 hours = $3,640 ID Consultant @ $50: 56 hours = $2,800 | $19,856 | $9,928 | $12,000 | $3,971.20 | $45,755 |
| 1.3.6 | EPSS Phase 2 Design | 416 | Developer 1 @ $35: 108 hours = $3,780 Developer 2 @ $35: 108 hours = $3,780 Josie @ $47: 48 hours = $2,256 Tim @ $47: 32 hours = $1,504 ID Consultant @ $50: 80 hours = $4,000 Barry @ $45: 40 hours = $1,800 | $17,120 | $8,560 | $12,000 | $3,424 | $41,104 |

| WBS No. | Activity Name | Work Effort/ Resource Hours | Resource Name Resource Rate per hour Resource Hours Resource Total Rate | Activity Estimate | Indirect Cost @ 50% of activity | Travel Cost | Reserve @ 20% of activity | Total Estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.3.7 | EPSS Phase 3 Design | 400 | Developer 1 @ $35: 100 hours = $3,500 Developer 2 @ $35: 100 hours = $3,500 Ellen @ $49: 64 hours = $3,136 Josie @ $47: 40 hours = $1,880 Tim @ $47: 40 hours = $1,880 ID Consultant @ $50: 56 hours = $2,800 | $16,696 | $8,348 | $12,000 | $3,339.20 | $40,383 |
| 1.3.8 | EPSS Phase 4 Design | 400 | Developer 1 @ $35: 100 hours = $3,500 Developer 2 @ $35: 100 hours = $3,500 Barry @ $45: 56 hours = $2,520 Josie @ $47: 64 hours = $3,008 ID Consultant @ $50: 80 hours = $4,000 | $16,528 | $8,264 | $12,000 | $3,305.60 | $40,098 |
| 1.3.9 | EPSS Phase 5 Design | 384 | Developer 1 @ $35: 92 hours = $3,220 Developer 2 @ $35: 92 hours = $3,220 Ellen @ $49: 48 hours = $2,352 Tim @ $47: 32 hours = $1,504 Josie @ $47: 40 hours = $1,880 ID Consultant @ $50: 80 hours = $4,000 | $16,176 | $8,088 | $12,000 | $3,235.20 | $39,499 |

| WBS No. | Activity Name | Work Effort/ Resource Hours | Resource Name Resource Rate per hour Resource Hours Resource Total Rate | Activity Estimate | Indirect Cost @ 50% of activity | Travel Cost | Reserve @ 20% of activity | Total Estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.4 | Project Management activities | 1204.8 | Davey @ $55: 1,204.8 hours = $60,240 | $60,240 | $30,120 | 0 | $12,048 | $102,408 |
| 1.5 | Project Closeout | 120 | Davey @ $55: 64 hours = $3,520 Ellen @ $49: 8 hours = $392 Barry @ $ 45: 8 hours = $360 Tim @ $47: 8 hours = $376 Josie @ $47: 8 hours = $376 Developer 1 @ $35: 8 hours = $280 Developer 2 @ $35: 8 hours = $280 ID Consultant @ $50: 8 hours = $400 | $5,984 | $2,992 | 0 | $1,196.80 | $10,173 |
| 1.5.6 | WidgetMart EPSS Completed – Total Cost Estimate |  |  | $188,257.60 | $94,128.5 | $60,000 | $37,020.52 | $379,407.40 |

Rationale Statement

_______________________________________________

Case # 25 – Designing an Electronic Performance Support System for WidgetMart

(Ertmer & Quinn, 2007)

The cost estimate for EPSS is developed using the bottom-up budgeting approach discussed in (Portny, Mantel, Meredith, Shafer, Sutton, & Kramer, 2008).  For this document’s reporting purposes, activities at the work package level, “the lowest level in the WBS” (PMBOK Guide, 2008, p.118) have been individually cost estimated and aggregated to their next, logical higher-level activities.  The cost estimate for each work package, is documented (and available) by team members responsible for the respective activities.

Assumptions

- The hourly labor rates are “slightly” based on the 2010 Bureau of Labor Statistics salary data for the respective skills/professions: developer, training development manager, project manager, HR consultant, Marketing consultant, and instructional design consultant.

- Team members Ellen, Josie, Barry, and Tim will be cross-trained to perform instructional design and delivery activities.  Additionally, since the team members do not have formal instructional design experience, an Instructional Design Consultant will be hired (as a contractor) for the project.

- The cost has taken into consideration, learning curve, vacation, sick days, travel time, and other non-projected related time.

- The CEO’s time is not included in the cost estimation although he is expected to participate in meetings and project approval activities as needed.

- Travel cost is estimated to be $60,000 allocated $12,000 per phase, per 3 people travelling, at $4,000 each.  Travel cost includes airfare, lodging, meals, and other expenses.  The cost however will vary depending on price of airfare at the time of travel.

- WidgetMart has a 50 percent indirect cost allocated per activity.  This cost includes training materials, administrative costs, overhead costs, any equipment required for the project, and other expenses such as conference room set up.

- This estimate will be adjusted throughout the project as needed.

References

PMBOK Guide (2008). A Guide to the Project Management Body of

Knowledge (PMBOK® Guide). (p. 118). 4th ed. Newton Square, PA: Project Management Institute, Inc.

Portny, S. E., Mantel, S. J., Meredith, J. R., Shafer, S. M., Sutton, M. M., & Kramer, B.

E. (2008). (ch. 5). Project Management: Planning, scheduling, and controlling projects. Hoboken, NJ: John Wiley & Sons, Inc.